## Sheet1
Planning
A1	Define required pre/post-processing filters	December – January	Tomy
A2	Who will do all GUIs and 3D visualization?		All
Architecture
B1	Proposal of Development Platform and Styles	December	Suren
B2	Specification of Development Platform	January 31	Suren, Matthias	B1
B3	Specification of Coding Standards	January 31	Suren, Matthias	B1
B4	Document the framework architecture	March 15	Suren
B5	Define Interfaces for Control loop		Suren, Andreas
B6	Define an output format (for Archiving)	April 31	Tomy, Suren
B7	Hinting algorithms for data pre-loading (large datasets)	July 31	Suren, Matthias
Infrastructure
C1	Acquire domain ufo.kit.edu and configure server	December	Andreas, Suren
C2	Trac system for UFO documentation and source management	December	Suren	B1, B2
C3	Commissioning of Control PC for ANKA	March 15	Suren
C3.1	Acceptable solution for data streaming at Raid (own FS)	April 15	Suren
C3.2	Develop RingBufferFS for data streaming if needed	May 31	Suren	C3.1
C3.3	Order Areca Raid with External and Internal connectors		Suren
C4	Test Connection with LSDF	April	Tomy
C4.1	Optimize connection with LSDF (~200-300MB/s)	April	Halil
C4.2	Become GPFS node in LSDF to get higher bandwidths	May	Tomy, Halil
C10	Second Generation of Computation Platform (PCIe 3.0, GPUs, ...)		Suren
Camera Support
D1	Driver for IPE Camera	February	Matthias, Suren
D1.1	Fast DMA Transfers for IPE Camera		Suren	DMA implementation in FPGA
D2	PCO Edge support under 64 bit Linux	March 15	Mathias
D3	Unified control interface for IPE/Photon Focus/PCO cameras	March 15	Matthias
D3.1	Unified frame grabbing interfaces	March 31	Matthias
D4	Adapt camera GUI to developed interface exposing all parameters	April 31	Matthias
D5	Tango/SPEC Integration
D5.1	Tango/SPEC Integration, Software Camera	March	Volker (?)
D5.2	Tango/SPEC Integration, PCO Camera		Volker (?)
D5.3	Tango/SPEC Integration, Unified Interface	May 31	Volker (?)	D3, D3.1
D6	Fast Reject (In software)	May 31	Mathias	D3, D3.1
PyHST
E1	Port PyHST to OpenCL	March 15	Matthias
E1.1	CPU version of PyHST/OpenCL	July 31	Matthias
E2	Data streaming support in PyHST	March 31	Tomas
E3	Detect the center of rotation	March	Mathias	E4
E4	Split PyHST into the C-library and Python bindings	March 31	Matthias
Framework
F1	Framework L1: Data readout & format/source abstraction	May 31	Halil	B4
F2	Framework L1: Data Storage	July 31	Halil	B4, B6
F3	Memory Manager (Architecture Definition)	May 1	Halil, Matthias
F3.1	Simple implementation (HDD->SDD->Mem->GpuMem)	May 31	Halil, Matthias	B4
F3.2	Advanced memory manager with hinting support	November	Halil? / Suren	B7
F4	Framework L1: OpenCL primitives	July 31	All as needed
F5	Framework L3: Framework scheduler & planner	July 31	Suren	B4, E4
Filters
G1	Framework L2: Adapt Tomography to Framework	July 31	Suren	B4
G2	Framework L2: Port Laminography to OpenCL and Framework	July 31	Anton	B4
G3	Framework L2: Noise Reduction Filter	?	Elena	B4
G4	Framework L2: Fourier Filters		Mathias	B4
G5	Framework L2: ---- Other Required Filters ----		Elena	B4, A1

G100	DFI Implementation		Anton	B4
G101	Algebraic Reconstruction		Alexey	B4

Visualization
H1	Online visualization (just some of reconstructed slices)		Matthias	F*, G*
H2	Rendering: Algorithms for large data sets		Anton
H3	Rendering: Tools – histograms, etc.		Anton

UI
I1	GUI Hardware Management: Clarification of / Communication with IMAGE beamline		Vladimir, Weiss
I1.1	GUI Hardware Management: Prototype		Vladimir
I1.2	GUI Hardware Management: Commissioning		Vladimir

Integration
J1	Framework Library: Integration	October 1	Suren, Anton
J2	Integrate with TANGO and ANKA infrastructure		Suren, Tomas, Tomy

Further Development
Z1	Update scheme for reconstruction of dynamic processes	November	Suren
Z2	Data reduction schemes to reduce PCIe bandwidth		Matthias, Uros
Z3	Assessment Algorithms for Feedback Control		Matthias, Uros

Milestones
1	IPE Camera		Suren	D1.1, D3, D4
2	Image Based Triggers in Radiography		Matthias	C3, D6
3	Fast Tomography (Streaming Setup)		Suren	C3, D2-4, E2-4
4	Control Application		Andreas	2, B4