Tomy, Suren
Hinting algorithms for data pre-loading (large datasets)
Suren, Matthias
Commissioning of Control PC for ANKA
Mathias
Tomy, Suren, Halil
Suren, Matthias, Anton
Acceptable solution for data streaming at Raid (own FS)
Order Areca Raid with External and Internal connectors
done
in progress
B4, E4
Halil, Matthias
Halil, Matthias
Halil? / Suren
Halil
Halil
Suren
Matthias / Suren
B4
Suren
Elena
Elena
UFO2
in progress
Tomography: Performance s
Tomography: F
F5.1
UFO2
Mathias
PyHST
Ufo2
Continuous Tomography
Z1
Update scheme for reconstruction of dynamic processes
November
Suren
Z2
Data reduction schemes to reduce PCIe bandwidth
Matthias, Uros
Z2
Z3
Integration
Sureb
Suren
Suren
Suren
Suren
Implement data reduction scheme for distribution
Suren
Suren, phd
H2
S Chilingaryan, 23.2.2011
Workplan WP3 “Data processing, evaluation and visualization”
D4
D5
D5.1
D5.2
D5.3
D6
B6
C3.2
C3.3
C4
C4.1
C4.2
C10
Adapt camera GUI to developed interface exposing all parameters
Tango/SPEC Integration
Tango/SPEC Integration, Software Camera
Tango/SPEC Integration, PCO Camera
Tango/SPEC Integration, Unified Interface
Fast Reject (In software)
Define an output format (for Archiving)
Develop RingBufferFS for data streaming if needed
Test Connection with LSDF
Optimize connection with LSDF (~200-300MB/s)
Become GPFS node in LSDF to get higher bandwidths
Second Generation of Computation Platform (PCIe 3.0, GPUs, ...)
April 31
March
May 31
May 31
April 31
May 31
April
April
May
Matthias
Volker (?)
Volker (?)
Volker (?)
Suren
Suren
Tomy
Halil
Tomy, Halil
Suren
D3, D3.1
D3, D3.1
C3.1
Data Management
UFO2?
UFO2
UFO2
Order Areca Raid Card with External and Internal connectors
Matthias
Tomy, Suren
Camera Support
D1
Driver for IPE Camera
February
Matthias, Suren
UFO2
B6
Define an output format (for Archiving)
April 31
Camera Support
D1
D1.1
D2
Driver for IPE Camera
Fast DMA Transfers for IPE Camera
PCO Edge support under 64 bit Linux
February
March 15
Matthias, Suren
Suren
Mathias
DMA implementation in FPGA
C4
C4.1
C4.2
C10
Test Connection with LSDF
Optimize connection with LSDF (~200-300MB/s)
Become GPFS node in LSDF to get higher bandwidths
Second Generation of Computation Platform (PCIe 3.0, GPUs, ...)
April
April
May
Tomy
Halil
Tomy, Halil
Suren
B4, B6
B7
B7
July 31
Infrastructure
C1
C2
Acquire domain ufo.kit.edu and configure server
Trac system for UFO documentation and source management
December
December
Andreas, Suren
Suren
B1, B2
Camera Support
C3.2
C3.3
C4
C4.1
C4.2
C10
Develop RingBufferFS for data streaming if needed
Test Connection with LSDF
Optimize connection with LSDF (~200-300MB/s)
Become GPFS node in LSDF to get higher bandwidths
Second Generation of Computation Platform (PCIe 3.0, GPUs, ...)
May 31
April
April
May
Suren
Suren
Tomy
Halil
Tomy, Halil
Suren
C3.1
C3.1
April 15
Suren
E1
E1.1
E2
Port PyHST to OpenCL
CPU version of PyHST/OpenCL
Data streaming support in PyHST
March 15
July 31
March 31
Matthias
Matthias
Tomas
Standalone PyHST & Laminography
Optimize tomography for AMD cards
E1.3
Suren
Optimized reconstruction kernel for Fermi
E1.2
D1.1
D2
D3
D3.1
D4
D5
D5.1
D5.2
D5.3
D6
Fast DMA Transfers for IPE Camera
PCO Edge support under 64 bit Linux
Unified control interface for IPE/Photon Focus/PCO cameras
Unified frame grabbing interfaces
Adapt camera GUI to developed interface exposing all parameters
Tango/SPEC Integration
Tango/SPEC Integration, Software Camera
Tango/SPEC Integration, PCO Camera
Tango/SPEC Integration, Unified Interface
Fast Reject (In software)
March 15
March 15
March 31
April 31
March
May 31
May 31
Suren
Mathias
Matthias
Matthias
Matthias
Volker (?)
Volker (?)
Volker (?)
DMA implementation in FPGA
D3, D3.1
D3, D3.1
E4
Split PyHST into the C-library and Python bindings
March 31
Matthias
Suren, Andreas
Tomas
Student
B7
B6
Hinting algorithms for data pre-loading (large datasets)
“Out of core (memory) computation”
July 31
Suren, Matthias
E1
E1.1
E2
E3
E4
Port PyHST to OpenCL
CPU version of PyHST/OpenCL
Data streaming support in PyHST
Detect the center of rotation
Split PyHST into the C-library and Python bindings
March 15
July 31
March 31
March
March 31
Matthias
Matthias
Tomas
Mathias
Matthias
E4
Framework
July 31
G1
G1.1
G1.2
G2
G3
G4
G5
Framework L2: Adapt Tomography to Framework
Tomography: Performance study & optimizations
Tomography of dynamic processes
Framework L2: Port Laminography to OpenCL and Framework
Framework L2: Noise Reduction Filter
Framework L2: Fourier Filters
Framework L2: ---- Other Required Filters ----
July 31
November
July 31
?
Matthias
Matthias
Matthias
Anton
Tomsk
Mathias
Tomsk
B4
B4,B5
B4
B4
B4, A1
Anton
Alexey
Acceptable solution for data streaming at Raid
Alternative algorithm development
Filters
G100
G101
DFI Implementation
Algebraic Reconstruction
Anton
Alexey
B4
B4
UFO2
UFO2
Mathias
Tomsk
Camera Support
D1
D1.1
D2
D3
D3.1
D4
D5
D5.1
D5.2
D5.3
D6
Driver for IPE Camera
Fast DMA Transfers for IPE Camera
PCO Edge support under 64 bit Linux
Unified control interface for IPE/Photon Focus/PCO cameras
Unified frame grabbing interfaces
Adapt camera GUI to developed interface exposing all parameters
Tango/SPEC Integration
Tango/SPEC Integration, Software Camera
Tango/SPEC Integration, PCO Camera
Tango/SPEC Integration, Unified Interface
Fast Reject (In software)
February
March 15
March 15
March 31
April 31
March
May 31
May 31
Matthias, Suren
Suren
Mathias
Matthias
Matthias
Matthias
Volker (?)
Volker (?)
Volker (?)
DMA implementation in FPGA
D3, D3.1
D3, D3.1
C3.3
C4
C4.1
C4.2
C10
Test Connection with LSDF
Optimize connection with LSDF (~200-300MB/s)
Become GPFS node in LSDF to get higher bandwidths
Second Generation of Computation Platform (PCIe 3.0, GPUs, ...)
April
April
May
Suren
Tomy
Halil
Tomy, Halil
Suren
E1
E1.1
E2
E3
E4
Port PyHST to OpenCL
CPU version of PyHST/OpenCL
Data streaming support in PyHST
Detect the center of rotation
Split PyHST into the C-library and Python bindings
March 15
July 31
March 31
March
March 31
Matthias
Matthias
Tomas
Mathias
Matthias
E4
E1
E1.1
E2
E3
E4
Port PyHST to OpenCL
CPU version of PyHST/OpenCL
Data streaming support in PyHST
Detect the center of rotation
Split PyHST into the C-library and Python bindings
March 15
July 31
March 31
March
March 31
Matthias
Matthias
Tomas
Mathias
Matthias
E4
July 31
G100
DFI Implementation
Anton
B4
E1.1
E1.2
E1.3
E2
E3
E4
Framework
F1
F2
F3
F3.1
F3.2
F4
F5
Filters
G1
G2
G3
G4
G5
CPU version of PyHST/OpenCL
Optimized reconstruction kernel for Fermi
Optimize tomography for AMD cards
Data streaming support in PyHST
Detect the center of rotation
Split PyHST into the C-library and Python bindings
Framework L1: Data readout & format/source abstraction
Framework L1: Data Storage
Memory Manager (Architecture Definition)
Simple implementation (HDD->SDD->Mem->GpuMem)
Advanced memory manager with hinting support
Framework L1: OpenCL primitives
Framework L3: Framework scheduler & planner
Framework L2: Adapt Tomography to Framework
Framework L2: Port Laminography to OpenCL and Framework
Framework L2: Noise Reduction Filter
Framework L2: Fourier Filters
Framework L2: ---- Other Required Filters ----
July 31
March 31
March
March 31
May 31
July 31
May 1
May 31
November
July 31
July 31
July 31
July 31
?
Matthias
Suren
Mathias
Matthias
All as needed
Anton
E4
B4
B4
B4
B4
B4
B4, A1
Matthias
Anton
Student Work
Suren
B4
November
Standalone PyHST & Laminography
Matthias
Matthias
Tomography of dynamic processes
G1.2
Framework L3: Automatically use all GPUs/CPUs
F5.1
Tomography: Performance study & optimizations
G1.1
Framework L3: Graph Optimizer
F5.2
Optimize tomography for AMD cards
E1.3
Suren
Optimized reconstruction kernel for Fermi
E1.2
Matthias
Tomsk
Matthias
B4,B5
GPU implementation of Laminography
E5
Matthias, Suren
Matthias, Halil
Matthias, Halil
Matthias, Suren
Matthias
Matthias
B4
C3
C3.1
March 15
April 15
Suren
Suren
Standalone PyHST & Laminography
Commissioning of Control PC for ANKA
Comment: PC+pco.edge needed at the end of the April shutdown
(1.5.2011 ??? Needs to be confirmed by Tomy)
D1.1
Fast DMA Transfers for IPE Camera
Suren
DMA implementation in FPGA
Camera Support
C10
D1
Driver for IPE Camera
February
Matthias, Suren
C3.3
Order Areca Raid Card with External and Internal connectors
Suren
C3.3
2 x GPU Server Platforms for 2012
2 x GPU Reconstruction Platforms for 2012
Matthias, Suren
C200
C
CX2
C200.1
Mathias
March 15
PCO Edge support under 64 bit Linux
D2
Volker (?)
Tango/SPEC Integration, PCO Camera
D5.2
D1
D1.1
D6
DMA implementation in FPGA
Suren
Fast DMA Transfers for IPE Camera
D1.1
C4.2
May
February
Driver for IPE Camera
Camera Support
Matthias
April 31
Tango/SPEC Integration
Adapt camera GUI to developed interface exposing all parameters
D5
D4
DX1
Suren
Finalize IPE Camera Drivers
UFO2?
Tomy, Halil
May
Become GPFS node in LSDF to get higher bandwidths
C4.2
D3, D3.1
Matthias
May 31
Fast Reject (In software)
Matthias
Matthias
Matthias
Mathias
April 31
March 31
March 15
March 15
Adapt camera GUI to developed interface exposing all parameters
Unified frame grabbing interfaces
Unified control interface for IPE/Photon Focus/PCO cameras
PCO Edge support under 64 bit Linux
D4
D3.1
D3
D2
D3, D3.1
D3, D3.1
Volker (?)
Volker (?)
May 31
May 31
Fast Reject (In software)
Tango/SPEC Integration, Unified Interface
Tango/SPEC Integration, PCO Camera
D6
D5.3
D5.2
H1
H2
H3
Data Management
D3, D3.1
Matthias
May 31
Fast Reject (In software)
D6
D3, D3.1
Volker (?)
Volker (?)
Volker (?)
May 31
March
Tango/SPEC Integration, Unified Interface
Tango/SPEC Integration, PCO Camera
Tango/SPEC Integration, Software Camera
D5.3
D5.2
D5.1
C3.1
Tomy, Halil
Halil
Tomy
Suren
Suren
May
April
April
May 31
April 31
Become GPFS node in LSDF to get higher bandwidths
Optimize connection with LSDF (~200-300MB/s)
Test Connection with LSDF
Develop RingBufferFS for data streaming if needed
Define an output format (for Archiving)
C4.2
C4.1
C4
C3.3
C3.2
B6
Suren, phd
Suren, phd
Suren, phd
Suren, phd
K1
K2
K3
K4
K5
H1, H2, H3
Tomy, Suren
April 31
Define an output format (for Archiving)
B6
Data Management
D3, D3.1
Matthias
May 31
Fast Reject (In software)
D6
D3, D3.1
Volker (?)
May 31
Tango/SPEC Integration, Unified Interface
D5.3
Suren
Tomy, Halil
Halil
Tomy
Suren
May
April
April
Second Generation of Computation Platform (PCIe 3.0, GPUs, ...)
Become GPFS node in LSDF to get higher bandwidths
Optimize connection with LSDF (~200-300MB/s)
Test Connection with LSDF
C10
C4.2
C4.1
C4
C3.3
HX1, HX2, HX3
UFO2
PhD
Implement webapp for handheld systems
KX5
UFO2
PhD
Implement webapp for normal systems
KX4
UFO2
PhD
Data reduction scheme of visualization module for network distribution
B6
KX3
UFO2
PhD
Define a storage strategy
KX2
Volker (?)
Tango/SPEC Integration, PCO Camera
D5.2
C3.1
Suren
May 31
Develop RingBufferFS for data streaming if needed
C3.2
Infrastructure
B6
B6
KX1
Draw architecture of data management
Suren
D3, D3.1
Volker (?)
May 31
Tango/SPEC Integration, Unified Interface
D5.3
Suren
C3.3
UFO2
UFO2
PhD
PhD
Implement webapp for handheld systems
Implement webapp for normal systems
KX5
KX4
UFO2
C3.1
Suren
Tomy, Suren
May 31
April 31
Develop RingBufferFS for data streaming if needed
Define an output format (for Archiving)
C3.2
B6
Data Management
Suren
Tomy, Halil
May
Second Generation of Computation Platform (PCIe 3.0, GPUs, ...)
Become GPFS node in LSDF to get higher bandwidths
C10
C4.2
UFO2
PhD
Implement webapp for handheld systems
KX5
UFO2
HX1, HX2, HX3
PhD
Data reduction scheme of visualization module for network distribution
KX3
Halil
April
Optimize connection with LSDF (~200-300MB/s)
C4.1
Define Requirements for Data Managment System
Tomy, Suren
September
UFO2
UFO2?
UFO2
UFO2
UFO2
UFO2
UFO2
UFO2
UFO2
UFO2
UFO2
UFO2
BX2
Anton
Rendering: Tools – histograms, etc.
Tomy, Suren
April 31
Define an output format (for Archiving)
B6
Volker (?)
Volker (?)
Matthias
March
April 31
Tango/SPEC Integration, PCO Camera
Tango/SPEC Integration, Software Camera
Tango/SPEC Integration
Adapt camera GUI to developed interface exposing all parameters
D5.2
D5.1
D5
D4
C3.1
Suren
May 31
April 31
Develop RingBufferFS for data streaming if needed
Define an output format (for Archiving)
C3.2
B6
HX3
Fast I/I
F*, G*
Matthias
Online visualization (just some of reconstructed slices)
Matthias
March 15
Unified control interface for IPE/Photon Focus/PCO cameras
D3
D3, D3.1
Volker (?)
May 31
Tango/SPEC Integration, Unified Interface
D5.3
Anton
Rendering: Algorithms for large data sets
Matthias
March 31
Unified frame grabbing interfaces
D3.1
D3, D3.1
May 31
Fast Reject (In software)
D6
C3.2
Fast I/O for Real-Time Data Streaming
CX2
Develop RingBufferFS for data streaming if needed
Fast I/O & Storage
RingBufferFS
C3.1
May 31
D3, D3.1
DMA implementation in FPGA
Suren
Matthias
Suren
Suren
May 31
February
Fast Reject (In software)
Fast DMA Transfers for IPE Camera
Driver for IPE Camera
DX1
Camera Support
C3.1
Suren
May 31
Develop RingBufferFS for data streaming if needed
C3.2
F*, G*
Anton
Matthias
Rendering: Algorithms for large data sets
Online visualization (just some of reconstructed slices)
Visualization
D3, D3.1
DMA implementation in FPGA
Matthias
Suren
May 31
February
Fast Reject (In software)
Fast DMA Transfers for IPE Camera
Driver for IPE Camera
Camera Support
Matthias
Matthias
Mathias
March 31
March 15
March 15
Unified frame grabbing interfaces
Unified control interface for IPE/Photon Focus/PCO cameras
PCO Edge support under 64 bit Linux
D3.1
D3
D2
D3, D3.1
D3, D3.1
Volker (?)
Volker (?)
Volker (?)
Matthias
May 31
May 31
March
April 31
Fast Reject (In software)
Tango/SPEC Integration, Unified Interface
Tango/SPEC Integration, PCO Camera
Tango/SPEC Integration, Software Camera
Tango/SPEC Integration
Adapt camera GUI to developed interface exposing all parameters
D6
D5.3
D5.2
D5.1
D5
D4
C3.1
LX1
Suren, Matthias
Implement RingBufferFS for data stored using LX1
Support writing to RAW devices in framework
LX2
LX1
I/O Optimization
Matthias
Support in hardware
Integration with LibUCA
DX1.3
Suren
Support of Fast Reject in IPE Camera drivers
DX1.2
DX6
DX1.1
DX1
Suren
Tomy, Halil
Become GPFS node in LSDF to get higher bandwidths
Z1
Matthias, Uros
UFO2
Matthias, Suren
Compression of
Suren, Anton
October 1
Framework Library: Integration
J1
Integration
HX1
HX1
Online visualization (just some of reconstructed slices)
Matthias
F*, G*
Anton
Rendering: Algorithms for large data sets
F*, G*
Matthias
Online visualization (just some of reconstructed slices)
Volker (?)
March
Tango/SPEC Integration, Software Camera
Tango/SPEC Integration
D5.1
D5
April 31
Define an output format (for Archiving)
B6
HX2
HX2
HX3
Data Management
HX1
Matthias, Uros
Data reduction schemes to reduce PCIe bandwidth
Z2
PhD
PhD
Implement webapp for handheld systems
Implement webapp for normal systems
KX5
KX4
Tomy, Suren
April 31
Define an output format (for Archiving)
B6
UFO2?
Tomy, Halil
May
Become GPFS node in LSDF to get higher bandwidths
C4.2
UFO2?
Implement Storage
PhD
Define a storage strategy
KX2
UFO2
PhD
Implement webapp for handheld systems
KX5
Tomy, Suren
April 31
Define an output format (for Archiving)
B6
Suren
Second Generation of Computation Platform (PCIe 3.0, GPUs, ...)
C10
KX1
LSDF-running software required for data management
Implement UFO Storage Format in Framework
KX4
KX2
Define a storage strategy
PhD
BX1
HX1, HX2, HX3
PhD
Data reduction scheme of visualization module for network distribution
KX3
PhD
PhD
Implement webapp for handheld systems
Implement webapp for normal systems
KX5
KX4
HX1, HX2, HX3
UFO2
PhD
Implement webapp for normal systems
KX4
UFO2
PhD
Data reduction scheme of visualization module for network distribution
KX3
HX1, HX2, HX3
Implement webapp for handheld systems
HX3
PhD
KX5
HX1, HX2, HX3
PhD
PhD
Implement webapp for normal systems
Data reduction scheme of visualization module for network distribution
KX4
KX3
UFO2?
Tomy, Halil
May
Become GPFS node in LSDF to get higher bandwidths
C4.2
Implement webapp for handheld devices
UFO2
PhD
Implement webapp for normal systems
KX4
KX3
PhD
Implement webapp for normal systems
KX4
PhD
Implement webapp for handheld systems
KX5
Draw design of Web-based Data Browser
Data reduction scheme of visualization module for network distribution
KX4
KX4
KX5
PhD
PhD
PhD
Implement webapp for normal systems
PhD
Data reduction scheme of visualization module for network distribution
PhD
PhD
Implement webapp for normal systems
KX5
KX4
HX1, HX2, HX3
PhD
Data reduction scheme of visualization module for network distribution
KX3
HX1, HX2, HX3
PhD
PhD
PhD
PhD
Implement webapp for handheld systems
Implement webapp for normal systems
Data reduction scheme of visualization module for network distribution
Define a storage strategy
KX5
KX4
KX3
KX2
UFO2
UFO2
UFO2
UFO2
HX1, HX2, HX3
PhD
PhD
PhD
PhD
Implement webapp for handheld systems
Implement webapp for normal systems
Data reduction scheme of visualization module for network distribution
Define a storage strategy
KX5
KX4
KX3
KX2
UFO2
C3.1
Suren
Tomy, Suren
May 31
April 31
Develop RingBufferFS for data streaming if needed
Define an output format (for Archiving)
C3.2
B6
Data Management
D3, D3.1
Matthias
May 31
Fast Reject (In software)
D6
Suren
Tomy, Halil
Halil
Tomy
May
April
April
Second Generation of Computation Platform (PCIe 3.0, GPUs, ...)
Become GPFS node in LSDF to get higher bandwidths
Optimize connection with LSDF (~200-300MB/s)
Test Connection with LSDF
C10
C4.2
C4.1
C4
KX4, KX5, HX3
Ph.D
Ph.D
KX6
Data reduction schemes for remote data presentation
Ph.D
Draw a design of Web-based Data Browser
KX4
KX5
Implement webapp for handheld devices
HX3, KX1, KX2
KX1
Halil
Software for automatic archival of data from UFO station
KX3
KX1
Halil
BX1
Halil
Implement UFO Storage Format
KX1
KX2
LSDF-running software Required for Data Management
HX1, HX2, HX3
UFO2
PhD
Implement webapp for handheld systems
KX5
UFO2
PhD
Implement webapp for normal systems
KX4
UFO2
PhD
Data reduction scheme of visualization module for network distribution
KX3
Data Management
UFO2?
Implement UFO Storage Format
Implement UFO Storage Format (Nexus?)
Define an output format (for Archiving)
Define an output format for Archiving (Nexus-based)
PhD
Implement webapp for handheld systems
KX5
C3.1
Suren
May 31
Develop RingBufferFS for data streaming if needed
C3.2
Tomy, Suren
April 31
Define an output format (for Archiving)
B6
G100
G101
C3.1
Suren
May 31
Develop RingBufferFS for data streaming if needed
C3.2
B4
Matthias
Algebraic Reconstruction
GX1
Anton
Anton
KX8
Monitor a
KX4, KX5, HX3
HX3, KX1, KX2
Ph.D
Ph.D
Ph.D
Implement webapp for handheld devices
Implement webapp for normal systems
Data reduction schemes for remote data presentation
Draw a design of Web-based Data Browser
KX6
KX5
KX4
B4
Matthias
Algebraic Reconstruction
GX1
Implement webapp for handheld devices
Implement webapp for normal systems
PhD
Data reduction scheme of visualization module for network distribution
PhD
PhD
Implement webapp for normal systems
KX5
KX4
HX1, HX2, HX3
PhD
PhD
PhD
Implement webapp for handheld systems
Implement webapp for normal systems
Data reduction scheme of visualization module for network distribution
KX5
KX4
KX3
HX1, HX2, HX3
PhD
PhD
PhD
Implement webapp for handheld systems
Implement webapp for normal systems
Data reduction scheme of visualization module for network distribution
KX5
KX4
KX3
C3.1
Suren
May 31
Develop RingBufferFS for data streaming if needed
C3.2
Tomy, Suren
April 31
Define an output format (for Archiving)
B6
UFO2
C3.1
Suren
May 31
Develop RingBufferFS for data streaming if needed
C3.2
UFO2?
Tomy, Halil
May
Become GPFS node in LSDF to get higher bandwidths
C4.2
KX4, KX5, HX3
KX4, KX5, HX3
Ph.D
Ph.D
Ph.D
KX7
KX6
Data reduction schemes for remote data presentation
Ph.D
Draw a design of Web-based Data Browser
KX4
KX5
Implement webapp for handheld devices
HX3, KX1, KX2
KX1
Halil
Software for automatic archival of data from UFO station
KX3
HX1, HX2, HX3
UFO2
PhD
Implement webapp for normal systems
KX4
UFO2
PhD
Data reduction scheme of visualization module for network distribution
KX3
UFO2?
Visualization
BX1
Monitor beam parameteres
Z2
Further Development
Z1
Matthias, Uros
Assessment Algorithms for Feedback Control
Further Development
B4
Matthias, Uros
Matthias
Assessment Algorithms for Feedback Control
Algebraic Reconstruction
GX1
Further Development
B4
B4
Matthias
Anton?
Algebraic Reconstruction
DFI Implementation
GX1
GX2
Filters - Alternative algorithm development
GX3
Augment
Further Development
Further Development
Further Development
Matthias, Uros
Assessment Algorithms for Feedback Control
Matthias, Uros
Assessment Algorithms for Feedback Control
Further Development
UFO2
UFO2
UFO2
Further Development
UI
Hardware GUI
Framework GUI
Hardware GUI
Vladimir
Vladimir
Vladimir, Weiss
GUI Hardware Management: Commissioning
GUI Hardware Management: Prototype
GUI Hardware Management: Clarification of
Communication with IMAGE beamline
I1.2
I1.1
I1
Further Development
Matthias, Uros
Assessment Algorithms for Feedback Control
Matthias, Uros
Assessment Algorithms for Feedback Control
Further Development
I1
I1.1
I1.2
Framework GUI
IX1
Integration of UFO Framework with standard
Framework GUI
Framework GUI (based on
Integration of UFO Framework with standard image processing tools
Vladimir, Weiss
GUI Hardware Management: Clarification of
Communication with IMAGE beamline
I1
Further Development
D3, D3.1
Support in hardware
DMA implementation in FPGA
Matthias
Matthias
Suren
Suren
Suren
Suren
Suren
May 31
February
April 31
Fast Reject (In software)
Integration with LibUCA
Support of Fast Reject in IPE Camera drivers
Fast DMA Transfers for IPE Camera
Driver for IPE Camera
Order Areca Raid Card with External and Internal connectors
Second Generation of Computation Platform (PCIe 3.0, GPUs, ...)
DX6
DX1.3
DX1.2
DX1.1
DX1
Camera Support
Vladimir
Vladimir
Vladimir, Weiss
GUI Hardware Management: Commissioning
GUI Hardware Management: Prototype
GUI Hardware Management: Clarification of
Communication with IMAGE beamline
I1.2
I1.1
I1
UI
Matthias, Uros
Assessment Algorithms for Feedback Control
Further Development
Matthias, Uros
Assessment Algorithms for Feedback Control
Matthias, Uros
Data reduction schemes to reduce PCIe bandwidth
DMA implementation in FPGA
Suren
Suren
February
Fast DMA Transfers for IPE Camera
Driver for IPE Camera
DX1
Camera Support
Tomy, Halil
Become GPFS node in LSDF to get higher bandwidths
F*, G*
Anton
Anton
Matthias
Rendering: Tools – histograms, etc.
Rendering: Algorithms for large data sets
Online visualization (just some of reconstructed slices)
H3
H2
H1
Visualization
Camera Support
Suren, Tomas, Tomy
Suren, Anton
October 1
Integrate with TANGO and ANKA infrastructure
Framework Library: Integration
J2
J1
Integration
Suren
Order Areca Raid Card with External and Internal connectors
C3.3
Matthias, Suren
February
Driver for IPE Camera
D1
Camera Support
DMA implementation in FPGA
Suren
Fast DMA Transfers for IPE Camera
D1.1
Matthias, Suren
February
Driver for IPE Camera
D1
Matthias
April 31
Adapt camera GUI to developed interface exposing all parameters
D4
Matthias, Uros
Data reduction schemes to reduce PCIe bandwidth
Z2
Define an output format for Archiving (Nexus-based?)
BX2, BX1
Suren, Ph.D.
Architecture of UFO Data Management System
Tomy, Suren, Halil
BX3
BX1
Architecture
Matthias
Support in hardware
Integration with LibUCA
DX1.3
Suren
Support of Fast Reject in IPE Camera drivers
DX1.2
DX1.1
CX1.1
CX1
Infrastructure
UFO2
B6
UFO2
PhD
Define a storage strategy
KX2
Tomy, Suren, Halil
Define Requirements for Data Management System
BX2
Rendering: Tools – histograms, etc.
Rendering: Algorithms for large data sets
Visualization
BX1
Halil
KX1
Data Management
Anton
Anton
Rendering: Tools – histograms, etc.
Rendering: Algorithms for large data sets
HX3
F*, G*
Matthias
Online visualization (just some of reconstructed slices)
Anton
Rendering: Tools – histograms, etc.
UFO2
UFO2
HX1, HX2, HX3
PhD
PhD
Data reduction scheme of visualization module for network distribution
Define a storage strategy
KX3
KX2
Tomy, Suren
April 31
Define an output format (for Archiving)
B6
D3, D3.1
Matthias
May 31
Fast Reject (In software)
D6
D3, D3.1
Volker (?)
Volker (?)
Volker (?)
Matthias
May 31
March
April 31
Tango/SPEC Integration, Unified Interface
Tango/SPEC Integration, PCO Camera
Tango/SPEC Integration, Software Camera
Tango/SPEC Integration
Adapt camera GUI to developed interface exposing all parameters
D5.3
D5.2
D5.1
D5
D4
C3.1
Halil
Tomy
Suren
Suren
April
April
May 31
April 31
Optimize connection with LSDF (~200-300MB/s)
Test Connection with LSDF
Develop RingBufferFS for data streaming if needed
Define an output format (for Archiving)
C4.1
C4
C3.3
C3.2
B6
C3, D6
Augmented Reality
Integration
J1
J2
Framework Library: Integration
Integrate with TANGO and ANKA infrastructure
October 1
Suren, Anton
Suren, Tomas, Tomy
HX1
HX2
HX3
HX4
HX5
Second Generation of Computation Platform (PCIe 3.0, GPUs, ...)
Visualization
KX4, KX5, HX3
KX4, KX5, HX3
LSDF
Rendering: Algorithms for large data sets
LX3
Become GPFS node in LSDF to get higher bandwidths
Tomy, Halil
Matthias
April 31
Adapt camera GUI to developed interface exposing all parameters
D4
Matthias, Suren
February
Driver for IPE Camera
D1
DMA implementation in FPGA
Suren
Fast DMA Transfers for IPE Camera
D1.1
Suren
Order Areca Raid Card with External and Internal connectors
C3.3
Matthias, Suren
February
Driver for IPE Camera
D1
D1.1
Fast DMA Transfers for IPE Camera
Suren
DMA implementation in FPGA
D4
Adapt camera GUI to developed interface exposing all parameters
April 31
Matthias
Camera Support
D4
Adapt camera GUI to developed interface exposing all parameters
April 31
Matthias
Camera Support
Camera Support
DX1
Driver for IPE Camera
Fast DMA Transfers for IPE Camera
February
Suren
Suren
DMA implementation in FPGA
D4
Adapt camera GUI to developed interface exposing all parameters
April 31
Matthias
D1
Driver for IPE Camera
February
Matthias, Suren
D1.1
Fast DMA Transfers for IPE Camera
Suren
DMA implementation in FPGA
D1
Driver for IPE Camera
February
Matthias, Suren
C3.3
Order Areca Raid Card with External and Internal connectors
Suren
Camera Support
Become GPFS node in LSDF to get higher bandwidths
Tomy, Halil
Camera Support
DX1
Driver for IPE Camera
Fast DMA Transfers for IPE Camera
February
Suren
Suren
DMA implementation in FPGA
Camera Support
DX1
DX1.1
DX1.2
Order Areca Raid Card with External and Internal connectors
Driver for IPE Camera
Fast DMA Transfers for IPE Camera
Support of Fast Reject in IPE Camera drivers
February
Suren
Suren
Suren
Suren
DMA implementation in FPGA
Support in hardware
GUI Hardware Management: Clarification of
Communication with IMAGE beamline
GUI Hardware Management: Prototype
GUI Hardware Management: Commissioning
Vladimir, Weiss
Vladimir
Vladimir
F*, G*
IX2
Matthias
Matthias
Framework GUI (based on VisTrails
IX3
Integration of UFO Framework with image processing tools (VisTrails)
IX2
IX1.2
IX1.1
IX1
GUI
DX1.1
CX1.1
IX1
IX1.1
IX1.2
IX2
IX3
Integration
J1
Framework Library: Integration
October 1
Suren, Anton
LX1
LSDF Integration
Become GPFS node in LSDF to get higher bandwidths
Integration
Data reduction schemes to reduce PCIe bandwidth
LX1
Supercomputing
LX2
Tomy, Halil
Rendering: Algorithms for large data sets
Become GPFS node in LSDF to get higher bandwidths
Tomy, Halil
Become GPFS node in LSDF to get higher bandwidths
Tomy, Halil
HX3
Ph.D
Ph.D
Ph.D
Ph.D
Ph.D
Ph.D
Matthias
Suren, Ph.D.
Matthias, Uros
Data reduction schemes to reduce PCIe bandwidth
Z2
Data reduction schemes to reduce PCIe bandwidth
Matthias, Uros
Z2
Data reduction schemes to reduce PCIe bandwidth
Matthias, Uros
Data reduction schemes to reduce PCIe bandwidth
Matthias, Uros
Assessment Algorithms for Feedback Control
Matthias, Uros
Further Development
Assessment Algorithms for Feedback Control
Matthias, Uros
April 31
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
Filters - Alternative algorithm development
GX1
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Algebraic Reconstruction
Halil
Halil
Halil
KX1
KX1
HX3, KX1, KX2
B4
Ph.D 2
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
KX4, KX5, H4
KX7, KX8
Ph.D 1
Integrate ADEI with UFO Data Management
KX9
MX*, KX1
Ph.D 1
Integrate monitored information into ADEI
KX8
BX1, MX1
Monitor beam parameters
MX2
Matthias, Suren
Record all relevant parameters (camera configs, motors, etc.)
MX1
Monitoring
Define an output format for Archiving (Nexus-based?)
Implement UFO Storage Format
KX4, KX5, HX3
KX4, KX5, HX3
Ph.D
Ph.D
Ph.D
KX7
KX6
Data reduction schemes for remote data presentation
Ph.D
Draw a design of Web-based Data Browser
KX4
KX5
Implement webapp for handheld devices
HX3, KX1, KX2
KX1
Halil
Software for automatic archival of data from UFO station
KX3
KX1
Halil
BX1
Halil
Implement UFO Storage Format
KX1
KX2
BX2, BX1
Suren, Ph.D.
Architecture of UFO Data Management System
LSDF-running software Required for Data Management
Tomy, Suren, Halil
BX3
BX1
Architecture
Filters - Alternative algorithm development
UFO2
HX1, HX2, HX3
UFO2
PhD
Implement webapp for handheld systems
KX5
UFO2
PhD
Implement webapp for normal systems
KX4
UFO2
PhD
Data reduction scheme of visualization module for network distribution
B6
KX3
UFO2
PhD
Define a storage strategy
KX2
Tomy, Suren, Halil
Define Requirements for Data Management System
BX2
Data Management
UFO2?
Ph.D, Halili
Suren
Matthias, Suren
scientist1
scientist1
scientist
Matthias, Suren, Uros
scientist1
scientist2
Suren, Matthias
Ph.D 2, Halili
Suren, Ph.D. 1
Tomy, Suren, Halil
Tomy, Suren, Halil
Tomy, Suren, Halil, scientist
scientist, Ph.D 1
2 x GPU Reconstruction Platform for 2012
GPU Final Reconstruction Platform 2014
Development Platform for 2012
3 Work
GPU Development Platform for 2012
Production Platform 2014
CUDA/PyHST/UFO Verification (is the system is fine)
CUDA/PyHST/UFO Verification (is the system is fine shape)
UFO should replace PyHST
July 31
Scientist, Tomy, Halil
Infini
C9
Infiniband Evaluation
DX2
Integrate with GPU
Support in hardware
May 31
November
July 31
Tomsk
?
F1
E1.5
Integrate tomography optimizations in UFO
Matthias
E1.3, E1.4
E1.5
G1.2
November
Tomography: Performance study & optimizations
C9.1
Suren
F6
F7
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
F6
Remotely executed modules (using Infiniband)
Matthias
Framework L1: Data Storage
F7
Anton?
Tomsk Students
DFI Reconstruction
G1.4
Tomas
March 31
Data streaming support in PyHST
E2
B4
?
Framework L2: Noise Reduction Filter
G3
Tomas
March 31
Data streaming support in PyHST
E2
Tomography of dynamic processes
Matthias
Tomsk Students
Algebraic Reconstruction
G1.5
Matthias, Suren
February
Driver for IPE Camera
D1
DMA implementation in FPGA
Suren
Fast DMA Transfers for IPE Camera
D1.1
Camera Support
Suren
Order Areca Raid Card with External and Internal connectors
C3.3
Matthias, Suren
February
Driver for IPE Camera
D1
D1.1
Fast DMA Transfers for IPE Camera
Suren
DMA implementation in FPGA
D1
Driver for IPE Camera
February
Matthias, Suren
D1.1
Fast DMA Transfers for IPE Camera
Suren
DMA implementation in FPGA
Camera Support
D1
Driver for IPE Camera
February
Matthias, Suren
C3.3
Order Areca Raid Card with External and Internal connectors
Suren
Become GPFS node in LSDF to get higher bandwidths
Tomy, Halil
Second Generation of Computation Platform (PCIe 3.0, GPUs, ...)
Order Areca Raid Card with External and Internal connectors
Suren
Suren
Vladimir, Weiss
GUI Hardware Management: Clarification of
Communication with IMAGE beamline
Suren
Order Areca Raid Card with External and Internal connectors
Tomy, Halil
Become GPFS node in LSDF to get higher bandwidths
Suren
Order Areca Raid Card with External and Internal connectors
C3.3
Matthias, Suren
February
Driver for IPE Camera
D1
DMA implementation in FPGA
Suren
Fast DMA Transfers for IPE Camera
D1.1
Matthias, Suren
February
Driver for IPE Camera
D1
DMA implementation in FPGA
Suren
Fast DMA Transfers for IPE Camera
D1.1
D1
Driver for IPE Camera
February
Matthias, Suren
C3.3
Order Areca Raid Card with External and Internal connectors
Suren
D1.1
Fast DMA Transfers for IPE Camera
Suren
DMA implementation in FPGA
D1
Driver for IPE Camera
February
Matthias, Suren
B4
Algebraic Reconstruction
GX1
Matthias
Remotely executed modules (using Infiniband)
GX6
Ph.D 2
Diffraction/Reflection Tomography
GX5
Ph.D 2
BX2, BX1
Suren, Ph.D.
Architecture of UFO Data Management System
BX3
CX1
Filters - Alternative algorithm development
GX3
GX1
Algebraic Reconstruction
Ph.D 2
B4
FX1
F5.2
Camera Support
Camera Support
Camera Support
DX1
Driver for IPE Camera
February
Suren
Vladimir
Vladimir
GUI Hardware Management: Commissioning
GUI Hardware Management: Prototype
Suren
February
Driver for IPE Camera
DX1
Camera Support
Camera Support
Camera Support
G6
G6.1
Filters
F5.2
Framework L3: Graph Optimizer
April 31
April 31
GX3
Assessment Algorithms for Feedback Control
Matthias, Uros
Filters - Alternative algorithm development
April 31
April 31
GX2
GX3
DFI Implementation
Assessment Algorithms for Feedback Control
Matthias, Uros
B4
F3.2
Advanced memory manager with hinting support
Matthias, Suren

Matthias, Suren
B4
Framework L3: Graph Optimizer
Advanced memory manager with hinting support
F3.2
FX2
Matthias, Suren
E4
Matthias
Mathias
Tomas
Matthias
Matthias
March 31
March
March 31
July 31
March 15
Split PyHST into the C-library and Python bindings
Detect the center of rotation
Data streaming support in PyHST
CPU version of PyHST/OpenCL
Port PyHST to OpenCL
E4
E3
E2
E1.1
E1
B4, A1
B4
B4
B4
Anton
?
July 31
July 31
Framework L2: ---- Other Required Filters ----
Framework L2: Fourier Filters
Framework L2: Noise Reduction Filter
Framework L2: Port Laminography to OpenCL and Framework
Framework L2: Adapt Tomography to Framework
G5
G4
G3
G2
G1
E4
Matthias
Mathias
Tomas
Matthias
Matthias
March 31
March
March 31
July 31
March 15
Split PyHST into the C-library and Python bindings
Detect the center of rotation
Data streaming support in PyHST
CPU version of PyHST/OpenCL
Port PyHST to OpenCL
E4
E3
E2
E1.1
E1
Tomography of dynamic processes
Matthias
Filters
G1
G1.1
G2
G3
Framework L2: Adapt Tomography to Framework
Tomography of dynamic processes
Framework L2: Port Laminography to OpenCL and Framework
Framework L2: Noise Reduction Filter
July 31
Matthias
Matthias
Matthias
Anton
B4
B4,B5
B4
C8,
Tomsk Students
Algebraic Reconstruction
G1.5
Tomsk Students
DFI Reconstruction
G1.4
Tomography: Performance study
G1.3
E1.3, E1.4
Matthias
Integrate tomography optimizations in UFO
G1.2
Tomsk, Matthias
June
Matthias
November
Matthias
Matthias
Tomography of dynamic processes
G1.2
Tomography: Performance study & optimizations
G1.1
Matthias
Tomsk
Matthias
B4,B5
G9
July 31
E4
Matthias
Mathias
Tomas
Matthias
Matthias
March 31
March
March 31
July 31
March 15
Split PyHST into the C-library and Python bindings
Detect the center of rotation
Data streaming support in PyHST
CPU version of PyHST/OpenCL
Port PyHST to OpenCL
E4
E3
E2
E1.1
E1
B4, A1
B4
B4
B4
Anton
?
July 31
July 31
Framework L2: ---- Other Required Filters ----
Framework L2: Fourier Filters
Framework L2: Noise Reduction Filter
Framework L2: Port Laminography to OpenCL and Framework
Framework L2: Adapt Tomography to Framework
G5
G4
G3
G2
G1
July 31
E4
Matthias
Mathias
Tomas
Matthias
Matthias
March 31
March
March 31
July 31
March 15
Split PyHST into the C-library and Python bindings
Detect the center of rotation
Data streaming support in PyHST
CPU version of PyHST/OpenCL
Port PyHST to OpenCL
E4
E3
E2
E1.1
E1
Tomography of dynamic processes
Matthias
Filters
G1
G1.1
G2
G3
G4
Framework L2: Adapt Tomography to Framework
Tomography of dynamic processes
Framework L2: Port Laminography to OpenCL and Framework
Framework L2: Noise Reduction Filter
Framework L2: Fourier Filters
July 31
Matthias
Matthias
Matthias
Anton
Matthias
B4
B4,B5
B4
B4
G1
G1.1
G1.2
G1.3
G2
G3
G4
G5
Framework L2: Adapt Tomography to Framework
Tomography: Performance study
Integrate tomography optimizations in UFO
Tomography of dynamic processes
Framework L2: Port Laminography to OpenCL and Framework
Framework L2: Noise Reduction Filter
Framework L2: Fourier Filters
Framework L2: ---- Other Required Filters ----
July 31
June
Matthias
Matthias
Matthias
Matthias
Anton
Tomsk, Matthias
Matthias
Matthias
B4
C8,
E1.3, E1.4
B4,B5
B4
B4
B4, A1
C8,
Matthias
Simulation of Tomography Data
G6
Tomsk Students
Algebraic Reconstruction
G1.5
Tomsk Students
DFI Reconstruction
G1.4
Tomography: Performance study
G1.3
E1.3, E1.4
Matthias
Integrate tomography optimizations in UFO
G1.2
G3
Matthias
Tomsk, Matthias
Optimize performance of Noise Reduction Filter
G3.1
June
Matthias
November
Matthias
Matthias
Tomography of dynamic processes
G1.2
Tomography: Performance study & optimizations
G1.1
Matthias
Tomsk
Matthias
B4,B5
Finish ISI Article
Matthias
Performance cou
Tomography: Performance study
Anton
Matthia, /Suren
Filters
G1.1
Tomography: Performance OpenCL/GLib performance counters
C8,
Filters
G1.1
F8
Filters
G1.1
Matthias
C8,
G1.1
Matthias
G1.1, G1.2, G2
E4
Matthias
Mathias
Tomas
Matthias
March 31
March
March 31
July 31
Split PyHST into the C-library and Python bindings
Detect the center of rotation
Data streaming support in PyHST
CPU version of PyHST/OpenCL
E4
E3
E2
E1.1
B4, A1
B4
B4
Anton
?
July 31
Framework L2: ---- Other Required Filters ----
Framework L2: Fourier Filters
Framework L2: Noise Reduction Filter
Framework L2: Port Laminography to OpenCL and Framework
G5
G4
G3
G2
E4
Matthias
Mathias
Tomas
Matthias
March 31
March
March 31
July 31
Split PyHST into the C-library and Python bindings
Detect the center of rotation
Data streaming support in PyHST
CPU version of PyHST/OpenCL
E4
E3
E2
E1.1
Tomography of dynamic processes
Matthias
Filters
G1
G1.1
G2
G3
Framework L2: Adapt Tomography to Framework
Tomography of dynamic processes
Framework L2: Port Laminography to OpenCL and Framework
Framework L2: Noise Reduction Filter
July 31
Matthias
Matthias
Matthias
Anton
B4
B4,B5
B4
G1.2
G1.3
G2
G3
G4
G5
Integrate tomography optimizations in UFO
Tomography of dynamic processes
Framework L2: Port Laminography to OpenCL and Framework
Framework L2: Noise Reduction Filter
Framework L2: Fourier Filters
Framework L2: ---- Other Required Filters ----
June
Matthias
Matthias
Anton
Tomsk, Matthias
Matthias
Matthias
E1.3, E1.4
B4,B5
B4
B4
B4, A1
G1.1
Matthias
C8,
G1.2
G1.3
G2
G3
G3.1
G4
G5
Integrate tomography optimizations in UFO
Tomography of dynamic processes
Framework L2: Port Laminography to OpenCL and Framework
Framework L2: Noise Reduction Filter
Optimize performance of Noise Reduction Filter
Framework L2: Fourier Filters
Framework L2: ---- Other Required Filters ----
June
Matthias
Matthias
Tomsk, Matthias
Matthias
Matthias
Matthias
E1.3, E1.4
B4,B5
B4
G3
B4
B4, A1
Anton, Matthias
C8,
Matthias
Simulation of Tomography Data
G6
Tomsk Students
Algebraic Reconstruction
G1.5
Tomsk Students
DFI Reconstruction
G1.4
Tomography: Performance study
G1.3
E1.3, E1.4
Matthias
Integrate tomography optimizations in UFO
G1.2
G3
Matthias
Tomsk, Matthias
Optimize performance of Noise Reduction Filter
G3.1
June
Matthias
November
Matthias
Tomography of dynamic processes
G1.2
Matthias
Tomsk
B4,B5
Matthias, Suren
February
Driver for IPE Camera
D1
Camera Support
Tomas
March 31
Data streaming support in PyHST
E2
Camera Support
Matthias
March 31
Split PyHST into the C-library and Python bindings
E4
E4
Mathias
Tomas
March
March 31
Detect the center of rotation
Data streaming support in PyHST
E3
E2
Matthias, Suren
February
Driver for IPE Camera
D1
Camera Support
E2
E3
E4
Data streaming support in PyHST
Detect the center of rotation
Split PyHST into the C-library and Python bindings
March 31
March
March 31
Suren
Mathias
Matthias
E4
Anton
Optimize tomography for AMD cards
E1.3
GPU implementation of Laminography
E5
Mathias
March 15
PCO Edge support under 64 bit Linux
D2
D3, D3.1
D3, D3.1
Volker (?)
Volker (?)
Volker (?)
Matthias
Matthias
Matthias
Mathias
May 31
May 31
March
April 31
March 31
March 15
March 15
Fast Reject (In software)
Tango/SPEC Integration, Unified Interface
Tango/SPEC Integration, PCO Camera
Tango/SPEC Integration, Software Camera
Tango/SPEC Integration
Adapt camera GUI to developed interface exposing all parameters
Unified frame grabbing interfaces
Unified control interface for IPE/Photon Focus/PCO cameras
PCO Edge support under 64 bit Linux
D6
D5.3
D5.2
D5.1
D5
D4
D3.1
D3
D2
E4
Matthias
Mathias
Tomas
Matthias
Matthias
March 31
March
March 31
July 31
March 15
Split PyHST into the C-library and Python bindings
Detect the center of rotation
Data streaming support in PyHST
CPU version of PyHST/OpenCL
Port PyHST to OpenCL
E4
E3
E2
E1.1
E1
B4, A1
B4
B4
B4
B4
B4
Anton
All as needed
?
July 31
July 31
July 31
July 31
November
May 31
May 1
July 31
May 31
Framework L2: ---- Other Required Filters ----
Framework L2: Fourier Filters
Framework L2: Noise Reduction Filter
Framework L2: Port Laminography to OpenCL and Framework
Framework L2: Adapt Tomography to Framework
Framework L3: Framework scheduler & planner
Framework L1: OpenCL primitives
Advanced memory manager with hinting support
Simple implementation (HDD->SDD->Mem->GpuMem)
Memory Manager (Architecture Definition)
Framework L1: Data Storage
Framework L1: Data readout & format/source abstraction
G5
G4
G3
G2
G1
Filters
F5
F4
F3.2
F3.1
F3
F2
F1
E4
Matthias
Mathias
Tomas
Matthias
Matthias
March 31
March
March 31
July 31
March 15
Split PyHST into the C-library and Python bindings
Detect the center of rotation
Data streaming support in PyHST
CPU version of PyHST/OpenCL
Port PyHST to OpenCL
E4
E3
E2
E1.1
E1
D3, D3.1
D3, D3.1
Volker (?)
Volker (?)
Volker (?)
Matthias
Matthias
Matthias
Mathias
May 31
May 31
March
April 31
March 31
March 15
March 15
Fast Reject (In software)
Tango/SPEC Integration, Unified Interface
Tango/SPEC Integration, PCO Camera
Tango/SPEC Integration, Software Camera
Tango/SPEC Integration
Adapt camera GUI to developed interface exposing all parameters
Unified frame grabbing interfaces
Unified control interface for IPE/Photon Focus/PCO cameras
PCO Edge support under 64 bit Linux
D6
D5.3
D5.2
D5.1
D5
D4
D3.1
D3
D2
Tomography of dynamic processes
Matthias
F5.2
Framework L3: Graph Optimizer
F3.2
Advanced memory manager with hinting support
Matthias, Suren
Filters
G1
G1.1
G2
G3
Framework L2: Adapt Tomography to Framework
Tomography of dynamic processes
Framework L2: Port Laminography to OpenCL and Framework
Framework L2: Noise Reduction Filter
July 31
Matthias
Matthias
Matthias
Anton
B4
B4,B5
B4
Filters
G1
G1.1
G1.2
G1.3
G2
G3
G4
G5
Framework L2: Adapt Tomography to Framework
Tomography: Performance study
Integrate tomography optimizations in UFO
Tomography of dynamic processes
Framework L2: Port Laminography to OpenCL and Framework
Framework L2: Noise Reduction Filter
Framework L2: Fourier Filters
Framework L2: ---- Other Required Filters ----
July 31
June
Matthias
Matthias
Matthias
Matthias
Anton
Tomsk, Matthias
Matthias
Matthias
B4
C8,
E1.3, E1.4
B4,B5
B4
B4
B4, A1
G1.1
Matthias
C8,
G1.1
Matthias
C8,
Matthias
Matthias
G1.2
G1.3
G2
G3
G3.1
G4
Integrate tomography optimizations in UFO
Tomography of dynamic processes
Framework L2: Port Laminography to OpenCL and Framework
Framework L2: Noise Reduction Filter
Optimize performance of Noise Reduction Filter
Framework L2: Fourier Filters
June
Matthias
Matthias
Tomsk, Matthias
Matthias
Matthias
E1.3, E1.4
B4,B5
B4
G3
B4
Framework
F1
F2
F3
F3.1
F4
F5
F5.1
Filters
G1
G1.2
G1.3
G2
G3
G3.1
G4
G5
Framework L1: Data readout & format/source abstraction
Memory Manager (Architecture Definition)
Simple implementation (HDD->SDD->Mem->GpuMem)
Framework L1: OpenCL primitives
Framework L3: Framework scheduler & planner
Framework L3: Automatically use all GPUs/CPUs
Framework L2: Adapt Tomography to Framework
Integrate tomography optimizations in UFO
Tomography of dynamic processes
Framework L2: Port Laminography to OpenCL and Framework
Framework L2: Noise Reduction Filter
Optimize performance of Noise Reduction Filter
Framework L2: Fourier Filters
Framework L2: ---- Other Required Filters ----
May 31
May 1
May 31
July 31
July 31
July 31
June
Matthias, Halil
Matthias, Halil
Matthias
Matthias
All as needed
Matthias, Suren
Matthias
Matthias
Matthias
Matthias
Anton, Matthias
Tomsk, Matthias
Matthias
Matthias
Matthias
B4
B4
B4
B4
B4
E1.3, E1.4
B4,B5
B4
G3
B4
B4, A1
G7.1
C8, G1.2, G2
F7.1, G1.2, G2
Anton, Matthias
Matthias, /Suren
Performance Evaluation
G7
OpenCL/GLib performance counters
Matthias
Get data from framework into the callback function
F7.1
Matthias
Embed framework in 3rd party applications using Unix pipes
F7
C8,
Framework L1: Data Storage (UFO Format)
Matthias
Support for prototyping modules in Python
F6
C9.2
Tomsk Students
Algebraic Reconstruction
G1.5
Tomsk Students
DFI Reconstruction
G1.4
Tomography: Performance study
G1.3
E1.3, E1.4
Matthias
Integrate tomography optimizations in UFO
G1.2
G3
Matthias
Tomsk, Matthias
Optimize performance of Noise Reduction Filter
G3.1
June
July
Matthias
High Speed Data Storage
F2.1
Matthias
B4
November
Matthias
Matthias
Tomography of dynamic processes
G1.2
Framework L3: Automatically use all GPUs/CPUs
F5.1
Tomography: Performance study & optimizations
G1.1
Framework L3: Graph Optimizer
F5.2
Matthias
Tomsk
Matthias
B4,B5
Matthias, Halil
Matthias, Halil
Matthias, Suren
Matthias
Matthias
July 31
Framework
B4
Anton
DFI Implementation
G100
July 31
Integration
J1
Framework Library: Integration
October 1
Suren, Anton
Suren, Tomas, Tomy
Suren, Anton
October 1
Integrate with TANGO and ANKA infrastructure
Framework Library: Integration
J2
J1
Integration
G4
G5
Framework L2: Fourier Filters
Framework L2: ---- Other Required Filters ----
Matthias
Matthias
B4
B4, A1
G6
Simulation of Tomography Data
Matthias
GUI
Rendering: Algorithms for large data sets
Rendering: Tools – histograms, etc.
GUI Hardware Management: Clarification of
Communication with IMAGE beamline
GUI Hardware Management: Prototype
GUI Hardware Management: Commissioning
Integration of UFO Framework with image processing tools (VisTrails)
Framework GUI (based on VisTrails
Vladimir, Weiss
Vladimir
Vladimir
Matthias
Matthias
F*, G*
IX2
I3
I2
I1.2
I1.1
I1
F*, G*
IX2
Matthias
Matthias
Framework GUI (based on VisTrails
IX3
Integration of UFO Framework with image processing tools (VisTrails)
IX2
IX1.2
IX1.1
IX1
GUI
Student Work
Augmented Reality for Control Applications
H6
Student Work
Utilization of 3D Displays, etc.
H5
Anton?
Anton?
HX1, HX2
Ph.D.
Rendering at lower resolution for remote devices
H4
H3
H2
F*, G*
Matthias
Online visualization (just some of reconstructed slices)
H1
Visualization
HX2
DX1.1
CX1.1
Matthias, Tomy
Check N1 at ANKA
Tomas/Tomy?
Remotely executed modules (using Infiniband)
Rendering: Algorithms for large data sets
Become GPFS node in LSDF to get higher bandwidths
Become GPFS node in LSDF to get higher bandwidths
Rendering: Algorithms for large data sets
Use cluster as acceleration node
Framework
FX3
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
GX6
Remotely executed modules (using Infiniband)
Matthias
DMA implementation in FPGA
Suren
Fast DMA Transfers for IPE Camera
D1.1
D1.1
Fast DMA Transfers for IPE Camera
Suren
DMA implementation in FPGA
D1.1
Fast DMA Transfers for IPE Camera
Suren
DMA implementation in FPGA
Become GPFS node in LSDF to get higher bandwidths
Tomy, Halil
Camera Support
Vladimir
Vladimir, Weiss
GUI Hardware Management: Prototype
GUI Hardware Management: Clarification of
Communication with IMAGE beamline
Camera Support
Tomy, Halil
Become GPFS node in LSDF to get higher bandwidths
DMA implementation in FPGA
Suren
Fast DMA Transfers for IPE Camera
D1.1
DMA implementation in FPGA
Suren
Fast DMA Transfers for IPE Camera
D1.1
D1.1
Fast DMA Transfers for IPE Camera
Suren
DMA implementation in FPGA
Tomas
Optical Flow
GX7
GX7
GX7.1
D3, D3.1
May 31
Fast Reject (In software)
D6
D6
Fast Reject (In software)
May 31
D3, D3.1
D3.1
Unified frame grabbing interfaces
March 31
Matthias
D6
Fast Reject (In software)
May 31
D3, D3.1
D3.1
Unified frame grabbing interfaces
March 31
Matthias
Rendering: Algorithms for large data sets
Anton
D6
Fast Reject (In software)
May 31
D3, D3.1
D3.1
Unified frame grabbing interfaces
March 31
Matthias
Rendering: Algorithms for large data sets
Anton
Suren
April 31
B4
Algebraic Reconstruction
Implement webapp for handheld devices
GX1
Filters - Alternative algorithm development
KX7
April 31
Filters - Alternative algorithm development
GX1
GX2
GX3
Algebraic Reconstruction
DFI Implementation
Assessment Algorithms for Feedback Control
Ph.D 2
Matthias, Uros
B4
B4
F3.2
Advanced memory manager with hinting support
Matthias, Suren
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias

Filters - Alternative algorithm development
GX1
GX2
Algebraic Reconstruction
DFI Implementation
Ph.D 2
B4
B4
Tomsk Student
Matthias
Remotely executed modules (using Infiniband)
GX6

Ph.D 2
Diffraction/Reflection Tomography
GX5
Ph.D 2
Ph.D 1
KX4, KX5, H4
KX7, KX8
Ph.D 1
Integrate ADEI with UFO Data Management
KX9
MX*, KX1
Ph.D 1
Integrate monitored information into ADEI
KX8
BX2, BX1
Suren, Ph.D.
Architecture of UFO Data Management System
BX3
Architecture
CX1
Filters - Alternative algorithm development
UFO2
GX3
Matthias, Suren
B4
Matthias
April 31
Tango/SPEC Integration
Adapt camera GUI to developed interface exposing all parameters
D5
D4
Matthias, Suren
February
Driver for IPE Camera
D1
DMA implementation in FPGA
Suren
Fast DMA Transfers for IPE Camera
D1.1
Camera Support
Suren
Order Areca Raid Card with External and Internal connectors
C3.3
Matthias, Suren
February
Driver for IPE Camera
D1
D1.1
Fast DMA Transfers for IPE Camera
Suren
DMA implementation in FPGA
D4
D5
Adapt camera GUI to developed interface exposing all parameters
Tango/SPEC Integration
April 31
Matthias
Camera Support
Driver for IPE Camera
February
D4
D5
Adapt camera GUI to developed interface exposing all parameters
Tango/SPEC Integration
April 31
Matthias
Camera Support
Driver for IPE Camera
February
Camera Support
DX1
Driver for IPE Camera
Fast DMA Transfers for IPE Camera
Fast Reject (In software)
February
May 31
Suren
Suren
Matthias
DMA implementation in FPGA
D3, D3.1
D4
Adapt camera GUI to developed interface exposing all parameters
April 31
Matthias
D1
Driver for IPE Camera
February
Matthias, Suren
D1.1
Fast DMA Transfers for IPE Camera
Suren
DMA implementation in FPGA
Camera Support
D1
Driver for IPE Camera
February
Matthias, Suren
C3.3
Order Areca Raid Card with External and Internal connectors
Suren
Camera Support
Become GPFS node in LSDF to get higher bandwidths
Tomy, Halil
Camera Support
DX1
Driver for IPE Camera
Fast DMA Transfers for IPE Camera
February
Suren
Suren
DMA implementation in FPGA
Camera Support
DX1
DX1.1
DX1.2
DX1.3
DX6
Second Generation of Computation Platform (PCIe 3.0, GPUs, ...)
Order Areca Raid Card with External and Internal connectors
Driver for IPE Camera
Fast DMA Transfers for IPE Camera
Support of Fast Reject in IPE Camera drivers
Integration with LibUCA
Fast Reject (In software)
February
May 31
Suren
Suren
Suren
Suren
Suren
Matthias
Matthias
DMA implementation in FPGA
Support in hardware
D3, D3.1
Vladimir
Vladimir
Vladimir, Weiss
GUI Hardware Management: Commissioning
GUI Hardware Management: Prototype
GUI Hardware Management: Clarification of
Communication with IMAGE beamline
Support in hardware
DMA implementation in FPGA
Suren
Suren
Suren
Suren
February
Support of Fast Reject in IPE Camera drivers
Fast DMA Transfers for IPE Camera
Driver for IPE Camera
Order Areca Raid Card with External and Internal connectors
DX1.2
DX1.1
DX1
Camera Support
DMA implementation in FPGA
Suren
Suren
February
Fast DMA Transfers for IPE Camera
Driver for IPE Camera
DX1
Camera Support
Tomy, Halil
Become GPFS node in LSDF to get higher bandwidths
Camera Support
Suren
Order Areca Raid Card with External and Internal connectors
C3.3
Matthias, Suren
February
Driver for IPE Camera
D1
DMA implementation in FPGA
Suren
Fast DMA Transfers for IPE Camera
D1.1
Matthias, Suren
February
Driver for IPE Camera
D1
Matthias
April 31
Adapt camera GUI to developed interface exposing all parameters
D4
DMA implementation in FPGA
Suren
Suren
February
Fast DMA Transfers for IPE Camera
Driver for IPE Camera
DX1
Camera Support
Camera Support
Matthias
April 31
Adapt camera GUI to developed interface exposing all parameters
D4
Camera Support
Matthias
April 31
Adapt camera GUI to developed interface exposing all parameters
D4
DMA implementation in FPGA
Suren
Fast DMA Transfers for IPE Camera
D1.1
D1
Driver for IPE Camera
February
Matthias, Suren
C3.3
Order Areca Raid Card with External and Internal connectors
Suren
D1.1
Fast DMA Transfers for IPE Camera
Suren
DMA implementation in FPGA
D1
Driver for IPE Camera
February
Matthias, Suren
D4
Adapt camera GUI to developed interface exposing all parameters
April 31
Matthias
Further Development
GX5
Diffraction/Reflection Tomography
Optical Flow
Ph.D 2
Tomas
Support in hardware
Suren
Support of Fast Reject in IPE Camera drivers
DX1.2
Matthias, Uros
Data reduction schemes to reduce PCIe bandwidth
Z2
Data reduction schemes to reduce PCIe bandwidth
Matthias, Uros
Z2
Data reduction schemes to reduce PCIe bandwidth
Matthias, Uros
Data reduction schemes to reduce PCIe bandwidth
Matthias, Uros
Assessment Algorithms for Feedback Control
Matthias, Uros
Further Development
Assessment Algorithms for Feedback Control
Matthias, Uros
April 31
B4
HX3, KX1, KX2
KX1
KX1
Halil
Halil
Halil
Algebraic Reconstruction
Implement webapp for handheld devices
Implement webapp for normal systems
Data reduction schemes for remote data presentation
Draw a design of Web-based Data Browser
Software for automatic archival of data from UFO station
LSDF-running software Required for Data Management
GX1
Filters - Alternative algorithm development
KX7
KX6
KX5
KX4
KX3
KX2
KX1
Data Management
April 31
Matthias, Uros
Assessment Algorithms for Feedback Control
Further Development
Matthias, Uros
Assessment Algorithms for Feedback Control
Matthias, Uros
Data reduction schemes to reduce PCIe bandwidth
Matthias, Uros
Data reduction schemes to reduce PCIe bandwidth
Z2
Matthias, Uros
Data reduction schemes to reduce PCIe bandwidth
Z2
Data reduction schemes to reduce PCIe bandwidth
Matthias, Uros
Filters - Alternative algorithm development
GX1
GX2
GX3
Algebraic Reconstruction
DFI Implementation
Assessment Algorithms for Feedback Control
Ph.D 2
Matthias, Uros
B4
B4
F3.2
Advanced memory manager with hinting support
Matthias, Suren
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias

Filters - Alternative algorithm development
GX1
GX2
Algebraic Reconstruction
DFI Implementation
Ph.D 2
B4
B4
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Filters - Alternative algorithm development
GX1
GX2
GX3
GX5
Algebraic Reconstruction
DFI Implementation
Assessment Algorithms for Feedback Control
Diffraction/Reflection Tomography
Optical Flow
Ph.D 2
Tomsk Student
Matthias, Uros
Ph.D 2
Tomas
B4
B4
GX6
Tomsk Student
Matthias
Remotely executed modules (using Infiniband)
GX6
Tomas
3D Optical Flow
GX6.1
Tomas
Optical Flow
GX7

Ph.D 2
Diffraction/Reflection Tomography
GX5
Ph.D 2
Ph.D 2
Ph.D 1
Ph.D 1
KX4, KX5, H4
KX4, KX5, H4
Optimization of postprocessing (segmentation, motion tracking, ...)
GX4
KX7, KX8
Ph.D 1
Integrate ADEI with UFO Data Management
KX9
MX*, KX1
Ph.D 1
Integrate monitored information into ADEI
KX8
Define an output format for Archiving (Nexus-based?)
BX2, BX1
Suren, Ph.D.
Architecture of UFO Data Management System
Tomy, Suren, Halil
BX3
BX1
Architecture
CX1
B4
B4
Matthias
Anton?
Algebraic Reconstruction
DFI Implementation
GX1
GX2
Filters - Alternative algorithm development
Infrastructure
UFO2
B6
UFO2
PhD
Define a storage strategy
KX2
Tomy, Suren, Halil
Define Requirements for Data Management System
BX2
GX3
Matthias, Suren
B4
Matthias, Suren
February
Driver for IPE Camera
D1
DMA implementation in FPGA
Suren
Fast DMA Transfers for IPE Camera
D1.1
Camera Support
Suren
Order Areca Raid Card with External and Internal connectors
C3.3
Matthias, Suren
February
Driver for IPE Camera
D1
D1.1
Fast DMA Transfers for IPE Camera
Suren
DMA implementation in FPGA
Camera Support
DX1
Driver for IPE Camera
February
Suren
D1
Driver for IPE Camera
February
Matthias, Suren
D1.1
Fast DMA Transfers for IPE Camera
Suren
DMA implementation in FPGA
Camera Support
D1
Driver for IPE Camera
February
Matthias, Suren
C3.3
Order Areca Raid Card with External and Internal connectors
Suren
Become GPFS node in LSDF to get higher bandwidths
Tomy, Halil
Camera Support
DX1
Driver for IPE Camera
February
Suren
Camera Support
DX1
DX1.1
Second Generation of Computation Platform (PCIe 3.0, GPUs, ...)
Order Areca Raid Card with External and Internal connectors
Driver for IPE Camera
Fast DMA Transfers for IPE Camera
February
Suren
Suren
Suren
Suren
DMA implementation in FPGA
Vladimir
Vladimir
Vladimir, Weiss
GUI Hardware Management: Commissioning
GUI Hardware Management: Prototype
GUI Hardware Management: Clarification of
Communication with IMAGE beamline
DMA implementation in FPGA
Suren
Suren
Suren
February
Fast DMA Transfers for IPE Camera
Driver for IPE Camera
Order Areca Raid Card with External and Internal connectors
DX1.1
DX1
Camera Support
Suren
February
Driver for IPE Camera
DX1
Camera Support
Tomy, Halil
Become GPFS node in LSDF to get higher bandwidths
Suren
Order Areca Raid Card with External and Internal connectors
C3.3
Matthias, Suren
February
Driver for IPE Camera
D1
DMA implementation in FPGA
Suren
Fast DMA Transfers for IPE Camera
D1.1
Matthias, Suren
February
Driver for IPE Camera
D1
Suren
February
Driver for IPE Camera
DX1
Camera Support
DMA implementation in FPGA
Suren
Fast DMA Transfers for IPE Camera
D1.1
D1
Driver for IPE Camera
February
Matthias, Suren
C3.3
Order Areca Raid Card with External and Internal connectors
Suren
D1.1
Fast DMA Transfers for IPE Camera
Suren
DMA implementation in FPGA
D1
Driver for IPE Camera
February
Matthias, Suren
GX5
Diffraction/Reflection Tomography
Optical Flow
Ph.D 2
Tomas
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
Data Management
KX1
KX2
KX3
KX4
KX5
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Tango/SPEC Integration
D5
D5
Tango/SPEC Integration
Driver for IPE Camera
February
D5
Tango/SPEC Integration
Driver for IPE Camera
February
Fast Reject (In software)
May 31
Matthias
D3, D3.1
DX1.3
DX6
Integration with LibUCA
Fast Reject (In software)
May 31
Matthias
Matthias
D3, D3.1
Further Development
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
MX*, KX1
KX7, KX8
KX7
KX8
KX9
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
Vladimir, Weiss
Vladimir
Vladimir
?
?
?
April 31
Infiniband Infrastructure
I1
I1.1
I1.2
GUI Hardware Management: Clarification of
Communication with IMAGE beamline
GUI Hardware Management: Prototype
GUI Hardware Management: Commissioning
Vladimir, Weiss
Vladimir
Vladimir
Tomy, Halil
Become GPFS node in LSDF to get higher bandwidths
I/O Optimization
LX1
LX2
Support writing to RAW devices in framework
Implement RingBufferFS for data stored using LX1
Data reduction schemes to reduce PCIe bandwidth
C3.1
LX1
J1
J2
Framework Library: Integration
Integrate with TANGO and ANKA infrastructure
October 1
Suren, Anton
Suren, Tomas, Tomy
Rendering: Algorithms for large data sets
Tomy, Halil
Become GPFS node in LSDF to get higher bandwidths
Tomy, Halil
Become GPFS node in LSDF to get higher bandwidths
Rendering: Algorithms for large data sets

Matthias, /Suren
Further Development
Further Development
Data Management
KX1
KX2
Implement UFO Storage Format
LSDF-running software Required for Data Management
Halil
Halil
BX1, MX1
KX1
MX2
Monitor beam parameters
Filters - Alternative algorithm development
GX1
GX2
Algebraic Reconstruction
DFI Implementation
Ph.D 2
Tomsk Student
B4
B4
H2
H3
H4
H5
H6
H2
Rendering: Algorithms for large data sets
Anton?
HX1
Anton?
Continuous Integration
MX2
Monitor beam parameters
Rendering: Algorithms for large data sets
Anton?
Anton?
H2
Real-time volume rendering (low quality)
H3
H2
Rendering: Algorithms for large data sets
Anton?
Rendering: Algorithms for large data sets
Framework
Integration
J1
Framework Library: Integration
October 1
Suren, Anton
Suren, Tomas, Tomy
Suren, Anton
October 1
Integrate with TANGO and ANKA infrastructure
Framework Library: Integration
J2
J1
Integration
Rendering: Algorithms for large data sets
Rendering: Tools – histograms, etc.
H4
H5
H6
Rendering at lower resolution for remote devices
Utilization of 3D Displays, etc.
Augmented Reality for Control Applications
Ph.D.
Student Work
Student Work
HX1, HX2
GUI
I1
I1.1
I1.2
I2
I3
GUI Hardware Management: Clarification of
Communication with IMAGE beamline
GUI Hardware Management: Prototype
GUI Hardware Management: Commissioning
Integration of UFO Framework with image processing tools (VisTrails)
Framework GUI (based on VisTrails
Matthias
Matthias
F*, G*
IX2
Tomas?
Tomas?
Tomas?
Student Work
Augmented Reality for Control Applications
H6
Student Work
Utilization of 3D Displays, etc.
H5
Anton?
Anton?
HX1, HX2
Ph.D.
Rendering at lower resolution for remote devices
H4
H3
H2
F*, G*
Matthias
Online visualization (just some of reconstructed slices)
H1
HX2
GUI Hardware Management: Clarification of
Communication with IMAGE beamline
GUI Hardware Management: Prototype
GUI Hardware Management: Commissioning
Vladimir, Weiss
Vladimir
Vladimir
Integration
J1
J2
Framework Library: Integration
Integrate with TANGO and ANKA infrastructure
October 1
Suren, Anton
Suren, Tomas, Tomy
B4
Storage Forma
Matthias
Summer 2012 (WP3)
Automn 2012 (WP3)
Autumn 2012 (WP3)
Storage Format
Compression
Continuous Integration
Implement simple control algorithm based on center of mass
Implement simple control algorithm based on center of mass
Matthias, Uros
Data reduction schemes to reduce PCIe bandwidth
Z2
Matthias, Suren
February
Driver for IPE Camera
D1
DMA implementation in FPGA
Suren
Fast DMA Transfers for IPE Camera
D1.1
Camera Support
Suren
Order Areca Raid Card with External and Internal connectors
C3.3
Matthias, Suren
February
Driver for IPE Camera
D1
D1.1
Fast DMA Transfers for IPE Camera
Suren
DMA implementation in FPGA
Camera Support
Z2
Data reduction schemes to reduce PCIe bandwidth
Matthias, Uros
D1
Driver for IPE Camera
February
Matthias, Suren
D1.1
Fast DMA Transfers for IPE Camera
Suren
DMA implementation in FPGA
Camera Support
D1
Driver for IPE Camera
February
Matthias, Suren
C3.3
Order Areca Raid Card with External and Internal connectors
Suren
Become GPFS node in LSDF to get higher bandwidths
Tomy, Halil
Camera Support
Assessment Algorithms for Feedback Control
Matthias, Uros
Camera Support
DX1
Second Generation of Computation Platform (PCIe 3.0, GPUs, ...)
Order Areca Raid Card with External and Internal connectors
Driver for IPE Camera
April 31
February
Suren
Suren
Suren
Vladimir
Vladimir
Vladimir, Weiss
GUI Hardware Management: Commissioning
GUI Hardware Management: Prototype
GUI Hardware Management: Clarification of
Communication with IMAGE beamline
Suren
Suren
February
Driver for IPE Camera
Order Areca Raid Card with External and Internal connectors
DX1
Camera Support
Camera Support
Tomy, Halil
Become GPFS node in LSDF to get higher bandwidths
Suren
Order Areca Raid Card with External and Internal connectors
C3.3
Matthias, Suren
February
Driver for IPE Camera
D1
DMA implementation in FPGA
Suren
Fast DMA Transfers for IPE Camera
D1.1
Matthias, Suren
February
Driver for IPE Camera
D1
Camera Support
DMA implementation in FPGA
Suren
Fast DMA Transfers for IPE Camera
D1.1
D1
Driver for IPE Camera
February
Matthias, Suren
C3.3
Order Areca Raid Card with External and Internal connectors
Suren
D1.1
Fast DMA Transfers for IPE Camera
Suren
DMA implementation in FPGA
D1
Driver for IPE Camera
February
Matthias, Suren
B4
HX3, KX1, KX2
KX1
KX1
Halil
Halil
Halil
Algebraic Reconstruction
Implement webapp for handheld devices
Implement webapp for normal systems
Data reduction schemes for remote data presentation
Draw a design of Web-based Data Browser
Software for automatic archival of data from UFO station
LSDF-running software Required for Data Management
GX1
Filters - Alternative algorithm development
KX7
KX6
KX5
KX4
KX3
KX2
KX1
Data Management
April 31
Matthias, Uros
Assessment Algorithms for Feedback Control
Matthias, Uros
Data reduction schemes to reduce PCIe bandwidth
Z2
Z2
Data reduction schemes to reduce PCIe bandwidth
Matthias, Uros
Filters - Alternative algorithm development
GX1
GX2
GX3
Algebraic Reconstruction
DFI Implementation
Assessment Algorithms for Feedback Control
Ph.D 2
Matthias, Uros
B4
B4
F3.2
Advanced memory manager with hinting support
Matthias, Suren
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias
FX2
Remotely executed modules (using Infiniband)
Matthias

Filters - Alternative algorithm development
GX1
GX2
GX3
GX5
Algebraic Reconstruction
DFI Implementation
Assessment Algorithms for Feedback Control
Diffraction/Reflection Tomography
Optical Flow
Ph.D 2
Matthias, Uros
Ph.D 2
Tomas
B4
B4
KX4
KX5
KX6
KX7
KX8
KX9
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Filters - Alternative algorithm development
GX1
GX2
GX3
GX5
Data Management
KX1
KX2
KX3
KX4
Algebraic Reconstruction
DFI Implementation
Assessment Algorithms for Feedback Control
Diffraction/Reflection Tomography
Optical Flow
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Ph.D 2
Tomsk Student
Matthias, Uros
Ph.D 2
Tomas
Halil
Halil
Halil
Ph.D 1
B4
B4
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
BX1, MX1
KX1
KX1
Data Management
KX1
KX2
KX3
KX4
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Halil
Halil
Halil
Ph.D 1
GX4
GX5
GX6
GX6.1
Optimization of postprocessing (segmentation, motion tracking, ...)
Diffraction/Reflection Tomography
Optical Flow
3D Optical Flow
Ph.D 2
Ph.D 2
Tomas
Tomas
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
I/O Optimization
LX1
LX2
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Support writing to RAW devices in framework
Implement RingBufferFS for data stored using LX1
Data reduction schemes to reduce PCIe bandwidth
Become GPFS node in LSDF to get higher bandwidths
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Tomy, Halil
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
C3.1
LX1
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
GX6
Tomsk Student
Matthias
Remotely executed modules (using Infiniband)
GX6
Tomas
3D Optical Flow
GX6.1
Tomas
Optical Flow
GX7

scientist
scientist
Ph.D 2
Diffraction/Reflection Tomography
GX5
Ph.D 2
Ph.D 2
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
KX4, KX5, H4
KX4, KX5, H4
Optimization of postprocessing (segmentation, motion tracking, ...)
GX4
KX7, KX8
Ph.D 1
Integrate ADEI with UFO Data Management
KX9
MX*, KX1
Ph.D 1
Integrate monitored information into ADEI
KX8
BX1, MX1
Monitor beam parameters
MX2
Matthias, Suren
Record all relevant parameters (camera configs, motors, etc.)
MX1
Monitoring
Define an output format for Archiving (Nexus-based?)
Implement UFO Storage Format
KX4, KX5, HX3
KX4, KX5, HX3
Ph.D
Ph.D
Ph.D
KX7
KX6
Data reduction schemes for remote data presentation
Ph.D
Draw a design of Web-based Data Browser
KX4
KX5
Implement webapp for handheld devices
HX3, KX1, KX2
KX1
Halil
Software for automatic archival of data from UFO station
KX3
KX1
Halil
BX1
Halil
Implement UFO Storage Format
KX1
KX2
scientist
C3.1
LX1
Suren, Matthias
Implement RingBufferFS for data stored using LX1
Support writing to RAW devices in framework
LX2
LX1
I/O Optimization
BX2, BX1
Suren, Ph.D.
Architecture of UFO Data Management System
LSDF-running software Required for Data Management
Tomy, Suren, Halil
BX3
BX1
Architecture
Support in hardware
Suren
Support of Fast Reject in IPE Camera drivers
DX1.2
LX4
CX1
B4
B4
Matthias
Anton?
Algebraic Reconstruction
DFI Implementation
GX1
GX2
Filters - Alternative algorithm development
Infrastructure
UFO2
HX1, HX2, HX3
UFO2
PhD
Implement webapp for handheld systems
KX5
UFO2
PhD
Implement webapp for normal systems
KX4
UFO2
PhD
Data reduction scheme of visualization module for network distribution
B6
KX3
UFO2
PhD
Define a storage strategy
KX2
Tomy, Suren, Halil
Define Requirements for Data Management System
BX2
Data Management
GX3
LX4
UFO2?
Matthias, Suren
B4
Module prototyping in python
C4.2
Become GPFS node in LSDF to get higher bandwidths
May
Tomy, Halil
C4.2
Become GPFS node in LSDF to get higher bandwidths
May
Tomy, Halil
B6
Define an output format (for Archiving)
April 31
Tomy, Suren
KX5
Implement webapp for handheld systems
PhD
KX5
Implement webapp for handheld systems
PhD
KX3
Data reduction scheme of visualization module for network distribution
PhD
HX1, HX2, HX3
C4.2
Become GPFS node in LSDF to get higher bandwidths
May
Tomy, Halil
KX3
KX4
Data reduction scheme of visualization module for network distribution
Implement webapp for normal systems
PhD
PhD
HX1, HX2, HX3
KX5
PhD
KX5
Implement webapp for handheld systems
PhD
KX4
Implement webapp for normal systems
PhD
KX5
Implement webapp for handheld systems
PhD
KX3
Data reduction scheme of visualization module for network distribution
PhD
HX1, HX2, HX3
KX4
KX5
Implement webapp for normal systems
PhD
PhD
Implement webapp for normal systems
B6
Define an output format (for Archiving)
April 31
Tomy, Suren
C3.2
Develop RingBufferFS for data streaming if needed
May 31
Suren
C3.1
KX5
Implement webapp for handheld systems
PhD
C3.2
Develop RingBufferFS for data streaming if needed
May 31
Suren
C3.1
C4.2
Become GPFS node in LSDF to get higher bandwidths
May
Tomy, Halil
B6
Define an output format (for Archiving)
April 31
Tomy, Suren
C3.2
Develop RingBufferFS for data streaming if needed
May 31
Suren
C3.1
KX5
Implement webapp for handheld systems
PhD
KX3
KX4
KX5
Data reduction scheme of visualization module for network distribution
Implement webapp for normal systems
Implement webapp for handheld systems
PhD
PhD
PhD
HX1, HX2, HX3
KX4
KX5
Implement webapp for normal systems
PhD
PhD
Implement webapp for normal systems
Implement webapp for handheld devices
GX1
Algebraic Reconstruction
Matthias
B4
KX6
Implement webapp for normal systems
Implement webapp for handheld devices
Ph.D
KX4, KX5, HX3
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
KX6
KX7
KX8
KX9
Implement UFO Storage Format
LSDF-running software Required for Data Management
Software for automatic archival of data from UFO station
Draw a design of Web-based Data Browser
Data reduction schemes for remote data presentation
Implement webapp for normal systems
Implement webapp for handheld devices
Integrate monitored information into ADEI
Integrate ADEI with UFO Data Management
Halil
Halil
Halil
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
Ph.D 1
BX1, MX1
KX1
KX1
HX3, KX1, KX2
KX4, KX5, H4
KX4, KX5, H4
MX*, KX1
KX7, KX8
Data Management
KX1
KX2
KX3
KX4
KX5
FX1
FX2
Visualization
Non-
Non-standard data types in the framework
Suren, Anton
October 1
Help Anton to port Laminography into the Framework
Matthias
## Workplan
Workplan WP3 “Data processing, evaluation and visualization”
S Chilingaryan, 26.07.2011				done
				high priority
				canceled
Planning
A1	Define required pre/post-processing filters	December – January	Tomy
A2	Who will do all GUIs and 3D visualization?		All

Architecture
B1	Proposal of Development Platform and Styles	December	Suren
B2	Specification of Development Platform	January 31	Suren, Matthias	B1
B3	Specification of Coding Standards	January 31	Suren, Matthias	B1
B4	Document the framework architecture	March 15	Suren
B5	Define Interfaces for Control loop		Matthias, Andreas
B6	UFO Storage Format		Matthias, Halil, Tomy, Suren

Infrastructure
C1	Acquire domain ufo.kit.edu and configure server	December	Andreas, Suren
C2	Trac system for UFO documentation and source management	December	Suren	B1, B2
C3	Commissioning of Control PC for ANKA	March 15	Suren
C3.1	Acceptable solution for data streaming at Raid	April 15	Suren
C4	Test Connection with LSDF	April	Tomy
C4.1	Optimize connection with LSDF (~200-300MB/s)	April	Halil
C5	CUDA//UFO Verification (is the system is fine shape)	March	Tomsk Students
C6	Autofix the CUDA problem requiring root run (do always?)	March	Tomsk Students
C7	OpenSuSE repository for UFO packages	March	Suren
C8	Replace PyHST with UFO as default recon. Tool	April	Matthias, Tomy, Wolfgang	F1, G5
C9	New storage system for UFO server		Suren
C9.1	Re-evaluate XFS Real-Time partition		Suren
C9.2	High speed storage library for camera and UFO		Suren

Camera Support
D2	PCO Edge support under 64 bit Linux	March 15	Mathias
D3	Unified control interface for IPE/Photon Focus/PCO cameras	March 15	Matthias
D3.1	Unified frame grabbing interfaces	March 31	Matthias
D4	Adapt camera GUI to developed interface exposing all parameters	April 31	Matthias
D5	Tango/SPEC Integration
D5.1	Tango/SPEC Integration, Software Camera	March	Volker (?)
D5.2	Tango/SPEC Integration, PCO Camera		Volker (?)
D5.3	Tango/SPEC Integration, Unified Interface	May 31	Volker (?)	D3, D3.1

Standalone PyHST & Laminography
E1	Port PyHST to OpenCL	March 15	Matthias
E1.1	CPU version of PyHST/OpenCL	July 31	Matthias
E1.2	Optimized reconstruction kernel for Fermi		Suren
E1.3	Optimize tomography for AMD cards		Student Work
E1.4	Optimize tomography for Kepler		Suren
E2	Data streaming support in PyHST	March 31	Suren
E3	Detect the center of rotation	March	Mathias	E4
E4	Split PyHST into the C-library and Python bindings	March 31	Matthias
E5	GPU implementation of Laminography		Anton

Framework
F1	Framework L1: Data readout & format/source abstraction	May 31	Matthias, Halil	B4
F2	Framework L1: Data Storage (UFO Format)		Matthias, Halil	B4, B6
F2.1	High Speed Data Storage	July	Matthias	C9.2
F3	Memory Manager (Architecture Definition)	May 1	Matthias
F3.1	Simple implementation (HDD->SDD->Mem->GpuMem)	May 31	Matthias	B4

F4	Framework L1: OpenCL primitives	July 31	All as needed
F5	Framework L3: Framework scheduler & planner	July 31	Matthias, Suren	B4
F5.1	Framework L3: Automatically use all GPUs/CPUs
F6	Support for prototyping modules in Python		Matthias
F7	Embed framework in 3rd party applications using Unix pipes		Matthias
F7.1	Get data from framework into the callback function		Matthias
G7	Performance Evaluation		Matthias, Suren	F7.1, G1.2, G2
G7.1	OpenCL/GLib performance counters		Matthias	C8, G1.2, G2

Filters
G1	Framework L2: Adapt Tomography to Framework	July 31	Matthias	B4
G1.2	Integrate tomography optimizations in UFO		Matthias	E1.3, E1.4
G1.3	Tomography of dynamic processes		Matthias
G2	Framework L2: Port Laminography to OpenCL and Framework	June	Anton, Matthias	B4,B5
G3	Framework L2: Noise Reduction Filter		Tomsk, Matthias	B4
G3.1	Optimize performance of Noise Reduction Filter		Matthias	G3
G4	Framework L2: Fourier Filters		Matthias	B4
G5	Framework L2: ---- Other Required Filters ----		Matthias	B4, A1
G6	Simulation of Tomography Data		Matthias

Visualization
H1	Online visualization (just some of reconstructed slices)		Matthias	F*, G*
H2	Low quality real-time 3D visualization		Matthias

GUI
I1	GUI Hardware Management: Clarification of / Communication with IMAGE beamline		Tomas?
I1.1	GUI Hardware Management: Prototype		Tomas?
I1.2	GUI Hardware Management: Commissioning		Tomas?
I2	Integration of UFO Framework with image processing tools (VisTrails)		Matthias	F*, G*
I3	Framework GUI (based on VisTrails		Matthias	IX2

Integration
J1	Framework Library: Integration
J2	Integrate with TANGO and ANKA infrastructure		Suren, Tomas, Tomy

Control
N1	Implement PID control algorithm based on center of mass		Matthias
N2	Integrate N1 with Tango and check at ANKA		Tomas?
N3	Checkout the limitations of Tango protocol (latency)	March	Tomas?

UFO2

Architecture
BX1	Define an output format for Archiving (Nexus-based?)		Halil, Tomy
BX2	Define Requirements for Data Management System		Scientist, Tomy, Halil
BX3	Architecture of UFO Data Management System		scientist, Ph.D. 1	BX2, BX1

Infrastructure
CX1	Second Generation of Computation Platform (PCIe 3.0, Kepler, ...)		Suren
CX1.1	Order Areca Raid Card with External and Internal connectors		Suren
CX1.2	High-speed Camera PC		Suren
CX1.3	Infiniband connection into the camera room		Andreas
CX2	Infiniband Infrastructure		Suren
CX2.1	Evaluation of Infiniband-based transports		Suren
CX2.2	Evaluation of GPU Direct		Suren
CX2.3	Evaluation of Infiiniband toolkits (MPI, mxqueue)		Matthias / Suren

Camera Support
DX1	Driver for IPE Camera	February	Suren
DX1.1	Fast DMA Transfers for IPE Camera		Suren	DMA implementation in FPGA
DX1.2	Support of Fast Reject in IPE Camera drivers		Suren	WP4
DX1.3	Integration with LibUCA		Matthias
DX2	Support High Precision Mode of IPE Camera		Suren	WP4
DX4	Check possibility of GPU Direct support		Suren	CX2.2
DX5	Integrate with Infiniband		Suren	CX2, WP4
DX6	Fast Reject (In software)		Matthias	D3, D3.1
DX7	Camera Simulation		Student, Suren
DX8	Direct data transfer from Camera to GPU		Suren, Matthias	FX2

Framework
FX1	Use remotely connected nodes (Infiniband) for acceleration		Matthias
FX2	Support non-standard data types in the filters		Matthias
FX3	L3: Graph Optimizer		Matthias
FX4	L3: Advanced memory manager with hinting support		Matthias

Filters - Alternative algorithm development
GX1	Algebraic Reconstruction		Ph.D 2	B4
GX2	DFI Implementation		Tomsk Student	B4
GX3	Assessment Algorithms for Feedback Control		Matthias, Uros
GX4	Optimization of postprocessing (segmentation, motion tracking, ...)		Ph.D 2
GX5	Diffraction/Reflection Tomography		Ph.D 2
GX6	Optical Flow		Tomas
GX6.1	3D Optical Flow		Tomas

Visualization
HX1	Rendering: Algorithms for large data sets		Ph.D
HX2	Rendering: Tools – histograms, etc.		Ph.D
HX3	Rendering at lower resolution for remote devices		Ph.D.	HX1, HX2
HX4	Utilization of 3D Displays, etc.		Student Work
HX5	Augmented Reality for Control Applications		Student Work

Data Management
KX1	Implement UFO Storage Format		Halil	BX1, MX1
KX2	LSDF-running software Required for Data Management		Halil	KX1
KX3	Software for automatic archival of data from UFO station		Halil	KX1
KX4	Draw a design of Web-based Data Browser		Ph.D 1
KX5	Data reduction schemes for remote data presentation		Ph.D 1	HX3, KX1, KX2
KX6	Implement webapp for normal systems		Ph.D 1	KX4, KX5, H4
KX7	Implement webapp for handheld devices		Ph.D 1	KX4, KX5, H4
KX8	Integrate monitored information into ADEI		Ph.D 1	MX*, KX1
KX9	Integrate ADEI with UFO Data Management		Ph.D 1	KX7, KX8

I/O Optimization
LX1	Support writing to RAW devices in framework		scientist	C3.1
LX2	Implement RingBufferFS for data stored using LX1		scientist	LX1
LX4	Data reduction schemes to reduce PCIe bandwidth		scientist
LX4	Become GPFS node in LSDF to get higher bandwidths		Tomy, Halil
LX5	Compression of stored data		scientist

Monitoring
MX1	Record all relevant parameters (camera configs, motors, etc.)		scientist, Matthias
MX2	Monitor beam parameters		scientist

Control
NX1	Tango replacement for real-time control
NX2	Verify precision of rotation stage

Further Development

Milestones
1	IPE Camera	April 31	Suren	D1.1, D3, D4
2	Image Based Triggers in Radiography	May 31	Matthias	C3, DX6
3	Fast Tomography (Streaming Setup)	May 31	Suren	C3, D2-4, E2-4
4	Control Application		Andreas	2, B4

Investments
1	GPU Development Platform
2	Development Place for IPE Camera
3	Development System for LSDF connection
4	3 Desktop Computers for Ph.Ds and scientist
5	Production Platform (2014)
6	Video-conferencing Hardware

## Quater Plans
Spring 2011 (WP3)
Prepare ISI Article	Suren
UFO should replace PyHST (installation + missing filters)	Matthias
Evaluation of Infiniband Architecture	Suren
Porting Laminography into the Framework	Anton
New Tomography Algorithms	Tomsk Students
High speed storage library	Suren
Evaluation of AMD NextGen architecture	Suren
Implement PID control algorithm based on center of mass	Matthias
Control Loop Demonstration	Matthias
Filter prototyping in python	Matthias
Establish OpenSuSE repository for UFO packages	Suren
System consistency check	Tomsk Students

Summer 2012 (WP3)
Fine-tune ISI Article	Suren
Tomography fine-tunning for Kepler architecture	Suren
Optimized tomography in Framework	Matthias
CPU/GPU Performance counters in Framework	Matthias
Tomography performance evaluation	Suren
New Tomography Algorithms	Tomsk Students
2D Visualization	Matthias
Test PID Control at ANKA	Tomas
Support non-standard data types in the framework (for camera and compressed formats)	Matthias

Autumn 2012 (WP3)
Continuous Integration
Compression
Storage Format
3D Visualization